## Before Grant Year End
|  |  | SRM |  |  | 2025-06-30 | <<< enter the grant's END DATE
2025-04-01 | 2025-05-01 | 2025-05-16 | 2025-05-31 | 2025-06-15 | 2025-06-30
DGM
Footnote : o Need for rebudgeting directs/indirects o Status of account number for upcoming budget period- new PTAEO string or Project Number o No-Cost Extension procedure and due date o Financial report due date o Ask about potential carry forward o Cost Share requirements
GUIDELINES TO GRANT CLOSE OUT
Timeline -- Before Grant Year End
Sets up advance account, if requested.
Works with the PI to determine if the award will be spent or if a no-cost extension will be requested. Reminds PI of any Progress Reports due prior to the end of the award budget period
Submits NCE request if applicable.
See Footnote for other items to review
Reminds subs of Final Invoice due date Works with PI on any needed progress reports
Begins closeout of encumbrances, personnel allocation shifts.
If needed, requests advance account for next year's award (if applicable)
Grant Ends

## Before FR submission
[5 empty] | 2025-06-30 | <<< enter grant's End Date
SRM
[5 empty] | 90 | <<< enter the # of days after end date to submit FFR (refer to your NOA)
[5 empty] | 2025-09-28 | FFR due date
| 2025-09-13 |  | 2025-09-21 | 2025-09-28
[5 empty] | 2025-09-13 | DGM submits Final DIRECT COST expenditure total to SRM (via RAPPORT) by this date
(ALL outstanding transactions had to have cleared the PTAEO by submission)
DGM
Footnote: o Final direct cost expenditures for the account o Zeroing out of encumbrances o Carry forward, or disposition of any remaining funds
GUIDELINES TO GRANT CLOSE OUT
Timeline - Before Financial Report/Invoice Submission
Puts the account into “pending close/on hold” status once final figures confirmed
SRM submits completed Closeout Packet for final financial report or invoice to sponsor
Confirms that outstanding transactions have posted and submits final figures to OSP/SRM
Financial report/Invoice Due date
DGM sends SRM final closeout information via "Request Award Modification" activity in RAPPORT
See Footnote